## AVCDL product RACI
|  |  |  | group |  |  |  |  | inputs
AVCDL phase | requirement | Title | NCWF role | security | devops | development | risk | project management | security | devops | development | risk | project management
Foundation | 1 | Training | cyber instructor | A | I | C | I |  | training subjects |  | list of programming languages / compilers
| 2 | Roles and Responsibilities | systems requirements planner | A | C | C |  |  | list of phase requirements
| 3 | Toolchain Support | information systems security developer | C | A | C |  |  | list of security tools / tool security criteria | component tracking system | list of development tools
| 4 | Definition of Security Requirements | systems requirements planner | A | I | I |  |  | global security goals / security taxonomy
| 5 | Protect the Code | information systems security developer | C | A |  |  |  | secure IP handling | secure IT infrastructure
| 6 | Ensure Release Integrity | information systems security developer | C | A | C |  |  | secure credential management recommendations | code signing / credential management / deployment infrastructure | credentials needed / integrity check availability
| 7 | Incident Response Plan | partner integration planner | A |  | C |  |  | incident tracking system |  | triage information required
| 8 | Decommissioning Plan | partner integration planner | A | C | C |  |  | secure wipe process | decommissioning / RMA process | list of data stored on systems
| 9 | Threat Prioritization Plan | systems requirements planner | A |  | I | R
| 10 | Deployment Plan | information systems security developer | C | A | C |  |  | secure deployment recommendations | deployment infrastructure / process | list material to be deployed
Requirements | 1 | Security Requirements Definition | security architect | A |  | I |  |  | product security goals / security taxonomy |  | high-level design / high-level requirements
| 2 | Requirements Gate | secure software assessor | R |  | R |  | A | all phase requirement products
Design | 1 | Apply Security Requirements and Risk Information to Design | software developer | R |  | A |  |  | security requirements catalog |  | detailed functional requirements
| 2 | Security Design Review | systems requirements planner | A |  | R | C |  |  |  | element detailed design
| 3 | Attack Surface Reduction | security architect | A |  | R |  |  |  |  | functional OS interface design
| 4 | Threat Modeling | security architect | A |  | R |  |  |  |  | element detailed design
| 5 | Design Gate | secure software assessor | R |  | R | R | A | all phase requirement products
Implementation | 1 | Use Approved Tools | software developer | C | C | A |  |  | tool selection criteria | component tracking comparison system | list of tools used
| 2 | Configure the Compilation and Build Process to Improve Executable Security | information systems security developer | C | A | C |  |  | secure build setting recommendations | build system | list of adopted secure build settings
| 3 | Use Secure Settings by Default | security architect | A |  | R |  |  | secure configuration recommendations |  | element detailed design
| 4 | Reuse Existing, Well-Secured Software When Feasible Instead of Duplicating Functionality | software developer | C | I | A |  |  |  |  | list of libraries used
| 5 | Create Source Code Adhering to Secure Coding Practice | software developer | C |  | A |  |  | secure coding recommendations |  | element implementation
| 6 | Deprecate Unsafe Functions | software developer | C |  | A |  |  | list of unsafe functions |  | list of deprecated functions in use
| 7 | Static Analysis | information systems security developer | C | A | C |  |  | secure static analysis setting recommendations | static analysis infrastructure / settings tracking | list of adopted security-related settings
| 8 | Dynamic Program Analysis | software developer | C |  | A |  |  | secure dynamic analysis tool recommendations | dynamic analysis testing infrastructure | list of adopted security-related tools
| 9 | Security Code Review | secure software assessor | A |  | C |  |  |  | code review infrastructure | element implementation
| 10 | Fuzz Testing | Vulnerability Assessment Analyst | A | C | C |  |  | fuzz testing recommendations | fuzz testing process infrastructure | element implementation
| 11 | Implementation Gate | secure software assessor | R | R | R |  | A | all phase requirement products
Verification | 1 | Penetration Testing | Vulnerability Assessment Analyst | A | C | C |  |  |  | penetration testing process infrastructure | operational system
| 2 | Threat Model Review | security architect | A |  | R |  |  |  |  | updated element detailed design
| 3 | Attack Surface Analysis Review | security architect | A |  | R |  |  |  |  | updated functional OS interface design
| 4 | Verification Gate | secure software assessor | R |  | R | R | A | all phase requirement products
Release | 1 | Final Security Review | secure software assessor | A | C | C | C |  |  |  | final design documentation
| 2 | Archive | information systems security developer |  | A | C |  |  |  | artifact storage infrastructure / tracking system | final materials for deployment
| 3 | Release Gate | secure software assessor | R | R | R | R | A | all phase requirement products
Operation | 1 | Identify and Confirm Vulnerabilities on an Ongoing Basis | Cyber Defense Forensics Analyst | A |  | C |  |  | incident tracking system |  | element detailed design
| 2 | Assess and Prioritize the Remediation of all Vulnerabilities | Cyber Defense Forensics Analyst | A |  | C | C |  | incident tracking system
| 3 | Analyze Vulnerabilities to Identify Their Root Causes | Cyber Defense Forensics Analyst | A |  | C |  |  | incident tracking system |  | element implementation
| 4 | Secure Deployment | information systems security developer | C | A | C |  |  | secure deployment recommendations | deployment infrastructure / process | materials for deployment
Decommissioning | 1 | Apply Decommissioning Protocol | information systems security developer | I | A |  |  |  | secure wipe process | decommissioning / RMA process | list of data stored on systems
Note: color highlight indicates accountable (A) group
| R | Responsible
| A | Accountable
| C | Consulted
| I | Informed